## Slide 1: Master Thesis Kick-off: Evaluating the Open-Source Market Model AMIRIS as a Substitute for Purchased Electricity Price Time Series
Supervisor: Rohith Krishnan Bala Krishnan
Presented by:
Muideen Oladayo Ajiboye (471583)
Date : 14 July 2026

## Slide 2: Thesis Plan & Approach

## Slide 3: Background & Objective
The need: the department’s Thuringia energy model requires hourly wholesale electricity price time series (8,760 prices/year, German bidding zone).
Status quo: these series are purchased from Energy Brainpool (Power2Sim scenario data).
The candidate: AMIRIS – DLR’s open-source, agent-based electricity market model – generates the same kind of hourly price series at no cost.
Thesis objective: understand AMIRIS in depth (inputs, internal process, outputs) and evaluate whether its output can credibly substitute the purchased data.
Research question: To what extent can AMIRIS reproduce German day-ahead price time series, and how does its accuracy compare with the commercially procured scenarios?

## Slide 4: AMIRIS in a Nutshell
Inputs (per year): hourly load, renewable feed-in profiles, power plant fleet (capacities, efficiencies, availabilities), fuel and CO2 prices, policy instruments.
Process: prototypical agents (plant operators, traders, storage, demand, exchange) bid into a simulated day-ahead auction; hourly merit-order clearing sets the price.
Outputs: hourly electricity prices, dispatch, technology market values, emissions, system costs.
Toolchain: Java/FAME engine configured via scenario.yaml, driven from Python (amirispy); one model year runs in under a minute.
Head start: a complete Germany2019 example ships with the model; DLR backtests reproduce the 2019 mean price closely (39.20 vs. 38.70 EUR/MWh).

## Slide 5: Methodology: Two Comparisons
Comparison 1 – Backtesting: AMIRIS vs. real EPEX/SMARD prices for historical years. Establishes whether the model is trustworthy; follows DLR’s published backtesting approach.
Comparison 2 – Benchmarking: AMIRIS vs. Energy Brainpool for a year covered by the department’s data – plus actual prices where the year already lies in the past.
Metrics: annual/monthly mean price, MAE, RMSE, correlation, price duration curves, daily and seasonal profiles, wind and PV capture prices, extreme hours (peaks, negative prices).
Key principle: both models compute conditional scenarios, not forecasts – the comparison targets price structure under given assumptions.

## Slide 6: Data & Tools
SMARD.de / ENTSO-E Transparency: real historical prices, load and feed-in data (free, official).
AMIRIS repository + amirispy: model code, Germany2019 example, documentation and wiki.
Energy Brainpool deliverables: the department’s purchased benchmark series (specification to be confirmed).
Python / pandas: one reusable comparison script (plots, error metrics, duration curves) applied to every model run.
Core literature: Schimeczek et al. 2023 (JOSS); Nitsch et al. backtesting studies for Germany and Austria 2019.

## Slide 7: Work Plan: 10 Weeks
Weeks 1–2 Toolchain setup; run and reproduce Germany2019; download real 2019 prices; build the pandas comparison script.
Weeks 3–4 Write the model description chapter while knowledge is fresh; obtain Brainpool data and confirm its specification.
Weeks 5–6 Parameterise one additional year (chosen by Brainpool coverage); backtest against actuals.
Weeks 7–8 Three-way analysis (AMIRIS vs. Brainpool vs. actuals); write methodology and results chapters.
Weeks 9–10 Discussion, introduction, conclusion, formatting; final 3–4 days reserved as buffer.
Writing rule: ~40% of total time on writing, distributed across all phases.

## Slide 8: Scope Decisions & Risk Management
In scope: Germany2019 baseline + one additional comparison year; deep three-way comparison.
Out of scope: gas-crisis years 2021/22 as main cases (discussion only); long-horizon (2030+) scenario comparisons; multi-country modelling.
Main risk: parameterising the additional year takes longer than planned (data gaps, fleet changes).
Mitigation: two-week timebox; fallback = keep 2019 as the single backtest year and deepen the Brainpool comparison instead.
Why this works: a clean, well-validated comparison on 1–2 years answers the department’s question better than a shallow one on many.

## Slide 9: Open Questions: Brainpool Data
1. Which years and delivery vintages does our Brainpool data cover?
2. Is it hourly (8,760 values/year) or aggregated?
3. Which scenario(s) were purchased (e.g. Central / Tensions / GoHydrogen)?
4. Exact price definition: German day-ahead, EUR/MWh, real or nominal terms?
5. File format, access, and any licensing limits for thesis use?
6. Does the Thuringia model consume the full hourly series or derived values (annual means, capture prices)?
Side note – Open-TYNDP: reviewed; it is a grid planning model (PyPSA-based), not a price model – useful as context and a source of scenario assumptions, not as a thesis tool.

## Slide 10: Next Steps & Requests
Requested today: sign-off on the scoped plan, choice of comparison year, and access to the Brainpool deliverables.
Starting immediately: toolchain setup and reproduction of the Germany2019 baseline (Weeks 1–2).
Proposed cadence: short bi-weekly progress check-ins; model description chapter as first written deliverable (end of Week 4).